## Summary
DataPilot Agent OS — Spec Completion Tracker
Reconciled directly against the running code (apps/api/app/routers/*.py, apps/web/app/components/*.tsx) and the live app, not against prior documentation claims.
Source: docs/IMPLEMENTATION_STATUS_MATRIX.md (eighteenth reconciliation pass, Sep 24 2026 — see §0 and the 'Sep 2026 Review' tab) + live verification on the Docker Compose stack.
Area | Total items tracked | Done | Partial | Not started / open | Notes
Core product workflows (§1) | 57 | 56 | 1 | 0 | Nearly everything a demo needs is real and working: auth/roles, file ingestion, catalog+search, SQL generation, quality, pipelines, lineage, agents, approvals, notebooks, Superset publish, security dashboard.
Enterprise readiness (§2) | 12 | 4 | 6 | 2 | SQL Server now has a self-contained Docker demo path. SSO, a real pen test, and a NetworkPolicy remain the big enterprise gaps.
Engineering / codebase health (§3) | 8 | 5 | 2 | 1 | Backend suite green (211 passed, 1 skipped, Sep 24 2026), web tsc clean and 7/7 source tests. Alembic migrations 0001-0006. Demo video still not recorded.
Metadata management (§4, direct Q&A) | 8 | 7 | 0 | 1 | One confirmed real gap: no first-class multi-data-model grouping per project (flat catalog + tags only).
This session — live bugs found in the running app | 2 | 0 | 2 | 0 | Both found by actually clicking through the app, not by reading code. See 'Bugs Found Live' tab.
September 2026 review (§0) | 76 | 69 | 3 | 4 | All review findings, Jev decisions, learning loop, analytics picker and the 16 agent/tool/gateway items are done and tested. Open items are user actions (rotate keys, change admin password, commit) and carried-over August items (SSO, pen test, demo video).
Legend
Done
Partial
Not started / open

## Sep 2026 Review
September 2026 Review — Closure Tracker
Devil's-advocate review of UI and API, Jev decision model, learning loop, embedded analytics and agent/tool hardening. Mirrors docs/IMPLEMENTATION_STATUS_MATRIX.md §0 (reconciled Sep 24, 2026; backend 211 passed / 1 skipped, web tsc clean).
Area | Item | Status | Evidence
Review findings (security, reliability, structure) | C1 app DB reachable from user/model SQL | ✅ | STAGING_DATABASE_URL → SELECT-only datapilot_reader; Postgres denies it users (verified live)
Review findings (security, reliability, structure) | C2 membership used instead of permission | ✅ | roles.py project role authoritative; viewer blocked from SQL/agents/tools
Review findings (security, reliability, structure) | C3 synchronous ask / lock across LLM calls | ✅ | SSE streaming POST /conversations/{id}/messages/stream; user turn written after generation
Review findings (security, reliability, structure) | C4 blocking calls in async endpoints | ✅ | run_in_threadpool on local agent paths
Review findings (security, reliability, structure) | H1 regex SQL guard | ✅ | sql_guard.py (sqlglot, per dialect) on every execution path
Review findings (security, reliability, structure) | H2 prompt injection | ✅ | Untrusted context fenced; catalogued relations only; repair then deterministic fallback
Review findings (security, reliability, structure) | H3 cache | ✅ | SQL only, never rows; TTL; failures never cached
Review findings (security, reliability, structure) | H4 silent provider fallback | ✅ | Per-purpose model_routes; unavailable routed provider → 409
Review findings (security, reliability, structure) | H5 approval not bound to plan | ✅ | Frozen plan + plan_hash, verified before every step
Review findings (security, reliability, structure) | H6 Temporal durability | ✅ | One activity per step, idempotency keys, deterministic workflow IDs
Review findings (security, reliability, structure) | M1–M6 (structure, migrations, hot paths, project pinning, auth/secrets, notebook freeze) | ✅ | core.py facade + services/; Alembic 0001–0006; indexes; X-Project-Id; httpOnly cookie + CSRF header; killable notebook cells
Review findings (security, reliability, structure) | Web review items (URLs, 401, cookie auth, a11y, dark mode, TanStack Query, App Router) | ✅ | app/(workspace)/… routes, lib/queries.tsx
Review findings (security, reliability, structure) | Frictionless (Open Knowledge Foundation) Data Package interchange | ✅ | GET /datapackage, /datasets/{id}/datapackage, validate, descriptive-only import
Chat, decisions and Jev | 3-panel Analysis chat rebuilt (threads · answer · inspector) | ✅ | ConversationsView.tsx; route, Jev decision, ensemble, learning sections in the inspector
Chat, decisions and Jev | Data-driven charts (KPI, line, bar, grouped/stacked bar, pie, scatter, table) with a switcher | ✅ | app/charts.py infer_chart; components/charts.tsx
Chat, decisions and Jev | Jev as a declared decision-model provider (typesafe/jev-1.13 via OpenRouter) | ✅ | Seeded when OPENROUTER_API_KEY is set; decision models can't serve generation purposes
Chat, decisions and Jev | Jev decides route and which agent / query tool | ✅ | Up to 3 agent options (decision_router.local_scores); catalog evidence in Jev's option text
Chat, decisions and Jev | Jev consequential-action check (escalate only) | ✅ | "Copy all customer records…" escalated at p ≈ 0.9 while rules missed it (live)
Chat, decisions and Jev | Jev picks the tool for each agent step | ✅ | _select_step_tools, jev_client.choose_tools; tool_choice evidence in the run trace
Chat, decisions and Jev | Jev SQL tie-break | ✅ | sql_candidate_judge on split votes
Chat, decisions and Jev | Router's chosen agent carried into the run | ✅ | agent_id on POST /agents/runs; lead agent owns a plan step
Chat, decisions and Jev | Measured accuracy | ✅ | 11 labelled routes: Jev 100% (~370 ms), keyword scorer 73%; earlier run Gemini 100% at 1075 ms
Chat, decisions and Jev | Tool-choice evaluation | ✅ | POST /router/evaluate-tools; Learning → Router panel
Chat, decisions and Jev | Usage per decision type | ✅ | GET /model-usage → by_purpose
Chat, decisions and Jev | Live proof report | ✅ | scripts/demo_jev_agents.py → docs/demo/; published proof page
Chat, decisions and Jev | Data residency (keep a project's decisions on-prem) | ✅ | Route decision purposes to the local deterministic model ("on-prem, no external call")
Learning loop and SQL | Verified-query memory (exact reuse, few-shot, 👍 capture, 👎 review) | ✅ | learning.py, routers/learning.py
Learning loop and SQL | GEPA prompt optimisation (offline, approval to activate) | ✅ | gepa.py; safety clause always appended
Learning loop and SQL | Multi-model SQL vote with semantic agreement | ✅ | learning.vote_candidates, results_agree
Learning loop and SQL | Cascade vote (the expensive third model only on disagreement) | ✅ | SQL_VOTE_MODE=cascade default; live: 2/2 agreement, Sonnet 5 not called
Learning loop and SQL | DDL is suggestion-only, driven by slow queries | ✅ | SLOW_QUERY_MS (500); ddl_suggestion artifacts; runs only with ALLOW_DDL_EXECUTION=true + approval
Learning loop and SQL | Profiled-only files broke SQL generation | ✅ Fixed | catalog_scope.py; Datasets "profile only" tag
Learning loop and SQL | Column / schema questions ran unrelated SQL | ✅ Fixed | catalog_answer.py: answered from catalog metadata, no SQL; "this / closest table" follows the conversation across sources
Learning loop and SQL | Rejected model SQL silently replaced by a generic fallback shown as PASSED | ✅ Fixed | Status "fallback" + the answer says the result may not answer the question
Learning loop and SQL | Follow-up after reload ran on the wrong source | ✅ Fixed | Source picker restores the conversation's last source
Learning loop and SQL | "Banking demo warehouse" was catalog-only (no credentials) | ✅ Fixed | Live RetailBanking DB in sqlserver-demo (infra/sqlserver-init/retail_banking.sql); connector wired to env:SQLSERVER_DEMO_CREDENTIALS
Learning loop and SQL | Query-tool suggestions from another source | ✅ Fixed | decide(..., connector_id) only offers tools for the selected source
Learning loop and SQL | SQL Server decimals stored as text (charts fell back to tables) | ✅ Fixed | charts.json_default keeps DECIMAL numeric
Learning loop and SQL | One-click "Publish to Superset" from a chat answer; resizable chat panels | ✅ | POST /analytics/publish-message; draggable History / Inspector widths
Embedded analytics (Superset) | "No address associated with hostname" | ✅ | Availability check + guidance; analytics profile documented
Embedded analytics (Superset) | Blank dashboards (charts taken by other dashboards, text-typed columns, dropped layout rows) | ✅ | Per-dashboard chart names, inferred column types, row wrapping; verified in Superset
Embedded analytics (Superset) | Dashboard picker: project dashboard, published queries, datasets by source | ✅ | GET /analytics/dashboards, POST /analytics/datasets/{id}/guest-token, SupersetView.tsx
Embedded analytics (Superset) | Scope and governance | ✅ | Project-scoped; restricted datasets admin-only; PII columns excluded; audited
Agents, tools and external gateway (16 items) | 1. Agent configuration read at run time (autonomy cap, provider pin, instructions) | ✅
Agents, tools and external gateway (16 items) | 2. Budget enforced (reflection counts; AGENT_RUN_MAX_SECONDS; PARTIALLY_SUCCEEDED) | ✅
Agents, tools and external gateway (16 items) | 3. Built-in tool timeouts; project-scoped sql.preview | ✅
Agents, tools and external gateway (16 items) | 4. Agent tool calls write ToolExecution rows | ✅ (verified live: 7 rows for one run)
Agents, tools and external gateway (16 items) | 5. Medium-risk tools only after human approval | ✅
Agents, tools and external gateway (16 items) | 6. HTTP egress: private-IP block, IP pinning, response cap | ✅
Agents, tools and external gateway (16 items) | 7. Separation of duties on approvals (APPROVAL_SEPARATION_OF_DUTIES) | ✅ (on in Kubernetes)
Agents, tools and external gateway (16 items) | 8. Agent publish gate (AGENT_PUBLISH_MIN_SCORE, audited admin force) | ✅
Agents, tools and external gateway (16 items) | 9. External client token expiry + last used (Alembic 0006) | ✅
Agents, tools and external gateway (16 items) | 10. Rate limiting no longer fails open; list + invoke limited | ✅
Agents, tools and external gateway (16 items) | 11. MCP ping, batch, notifications, JSON-RPC errors | ✅ (streamable HTTP GET/SSE not done)
Agents, tools and external gateway (16 items) | 12. Per-grant daily quota | ✅
Agents, tools and external gateway (16 items) | 13. Permission check on /query-tools/{id}/test | ✅
Agents, tools and external gateway (16 items) | 14. Jev judges split votes | ✅
Agents, tools and external gateway (16 items) | 15. Tool-choice evaluation | ✅
Agents, tools and external gateway (16 items) | 16. Data residency option | ✅
Learning, building, agents, graphs and consolidation (Sep 24–25) | Plan-guided query tuner: equivalence-checked rewrites (up to 6–8 attempts), no index creation, apply only via approval | ✅ | query_tuner.py, POST /sql/tune, Learning → Performance; live: 2.71 → 1.98 ms (27%) with 3 equivalent attempts
Learning, building, agents, graphs and consolidation (Sep 24–25) | Paste & run any-length SQL, plan analysis in plain language, full / piece-wise (per-CTE) rewrite | ✅ | POST /sql/run, POST /sql/analyze; 1,000+ line query ran live; piece-wise rewrite accepted only if the whole result matches
Learning, building, agents, graphs and consolidation (Sep 24–25) | Build very large SQL from business logic (plan → per-step build + repair → one WITH query) | ✅ | sql_composer.py, /sql/compose/*, SQL → Build from business logic; 65-step plan in tests, 7-step plan live
Learning, building, agents, graphs and consolidation (Sep 24–25) | Reviewer agent: every chat answer gets ok / check / doubtful with checks + Jev probabilities | ✅ | answer_review.py; live verdict ok 0.90 via Jev
Learning, building, agents, graphs and consolidation (Sep 24–25) | Draft with AI for new agents and query tools (registry-only tools) | ✅ | agent_designer.py, POST /agents/draft, POST /query-tools/draft; Jev + design model picks, validated
Learning, building, agents, graphs and consolidation (Sep 24–25) | Interactive charts: drill down/up, legend toggle, zoom, fullscreen; drill beyond the rows asks a follow-up | ✅ | charts.tsx (onDrill wired in Analysis)
Learning, building, agents, graphs and consolidation (Sep 24–25) | Relationship graph: pan/zoom/drag, focus, source → table → column drill, search, force/hierarchy layout | ✅ | GraphCanvas.tsx, RelationshipExplorer.tsx
Learning, building, agents, graphs and consolidation (Sep 24–25) | Consolidation: five nav areas, role defaults + "Show advanced", Agents & tools merged, Learning holds all feedback loops, Home opens Analysis, missing safety buttons, one "Save as…" menu | ✅ | docs/UX_CONSOLIDATION.md; /tools and /evaluations redirect
Learning, building, agents, graphs and consolidation (Sep 24–25) | Admin → Screens: hide pages or single tabs per project (e.g. for demos); presentation only, audited | ✅ | screen_visibility.py, GET/PUT /ui/screens, ScreenVisibilityPanel.tsx
Learning, building, agents, graphs and consolidation (Sep 24–25) | Jobs → Retry for tuning / composition / prompt-optimisation jobs | ✅ Fixed | Returns where to re-run instead of starting an agent
Still open | Rotate the Gemini and OpenRouter API keys shared in chat | 🔴 User action | Keys are only in the gitignored .env
Still open | Change the seeded admin's temporary password | 🔴 User action | The forced "change temporary password" dialog still appears
Still open | Commit this work | 🔴 User action | Nothing has been committed
Still open | MCP streamable HTTP (GET/SSE) | 🟡 By choice | POST JSON-RPC covers current clients
Still open | AgentVersion.input_schema / config at run time | 🟡 | Stored, not yet used
Still open | Timed-out built-in tool threads | 🟡 By design | Interrupted at the database; the thread can't be killed
Still open | Items carried from August (§2): PingFederate SSO, pen test, demo video, connector certification beyond SQL Server | 🔴 Unchanged | Outside this review's scope

## Core Workflows
1. Core Product Workflows
The demo-critical surface area — auth, ingestion, catalog, SQL generation, quality, pipelines, lineage, agents, approvals, notebooks, Superset, security.
Capability | Status | Evidence
Local auth, roles, project scoping | Done | /auth/*, /admin/users, /projects/*
File upload/profile/mapping/staging (CSV, JSON, Excel, Parquet) | Done | /files/*, versioned replace/append/key-merge load modes
Bulk catalog metadata import (CSV, no live data required) | Done | POST /datasets/import — creates/updates DataAsset rows, metadata_status="manual_import"
Catalog + hybrid search (Postgres keyword + Qdrant vector) | Done | /search, /datasets, /recommendations
Manual metadata edit/enrichment (description, tags, owner, sensitivity, freshness, status) | Done | PUT /datasets/{asset_id} — admin/engineer-gated, audited; edit modal covers all 6 fields
Column-level business names/descriptions | Done | column_notes on PUT /datasets/{asset_id}, feeds SQL-generation grounding text and catalog search relevance
SOP / business-glossary document upload (PDF or text) for grounding | Done | POST/GET/DELETE /glossary, chunked+indexed into vector store, retrieved by SQL generation and agent planner. Backend-only, no dedicated upload UI yet
Database connection via native driver or MCP | Done | POST /connectors, connection_mode: direct or mcp
Metadata scan for MCP-connected sources | Done | discover_mcp_metadata() — verified end-to-end against a local MCP fixture server
Catalog-grounded, dialect-aware SQL generation | Done | /sql/generate, /sql/execute — single read-only SELECT/WITH enforced
SQL-generation relevance for large catalogs (>40 tables) | Done | Real bug fixed — prioritized_catalog now threaded to the real-provider prompt path too, not just local-mock
SQL query history | Done | GET /sql/history
PII detection + output masking | Done | app/pii.py wired into local SQL execution, connector queries (incl. MCP), and file-ingestion column annotation
Persistent conversations with memory/summary | Done | /conversations/*
Data quality rules, runs, quarantine, remediation | Done | /quality/*
Pipeline generation + PostgreSQL view deployment | Done | /pipelines/*, approval-gated deploy
dbt/Dataform package emission | Partial | Real codegen exists (~1,100 lines, per-target archive/delivery-config/validate endpoints) but never test-run against an actual dbt CLI / Dataform project
Lineage — flat list/audit view | Done | GET /lineage
Lineage — multi-hop traversal | Done | GET /lineage/graph — bounded BFS traversal, depth 1-20, hop-depth + directioned edges
Semantic relationship graph (catalog/join relationships) | ✅ Real cross-source bug fixed, then corrected further for MCP connectors — see seventeenth-pass change-log entry | GET /semantic/graph — nodes from DataAsset, edges from governed SemanticJoinPolicy plus inferred column-name-matched suggestions flagged governed: false for review. Was suggesting joins across completely different external connectors (e.g. a Postgres warehouse and a SQL Server warehouse that both happen to have a customer_id column) purely because column names matched, with no notion that /sql/generate//sql/execute are always scoped to one connector (or the local workspace) at a time — those joins can never actually execute. User caught this live, from the graph rendering as a dense, near-fully-connected mesh with no visible structure. Fixed (fifteenth pass): inferred edges confined to assets that share a group_key(), each node carries a new group/source_label field, and the frontend clusters nodes into per-source arcs with distinct colors and a legend instead of one flat ring; POST/PUT /semantic/joins (validate_semantic_join_policy()) rejects a governed policy across two different connectors (422). User caught a second, deeper issue (seventeenth pass): that connector-level grouping is only correct for direct-driver connectors. An MCP-backed connector's assets are individually-discovered *tools* (discover_mcp_metadata() hardcodes schema_name="mcp" regardless of what backend a tool actually fronts), MCP execution invokes exactly one named tool per call with zero cross-tool join path anywhere in the runtime, and a single MCP toolbox can front more than one physically distinct backend (confirmed via infra/mcp-toolbox/toolbox.yaml's two separate kind: source blocks) — so two tools on the very same connector must never be treated as joinable either. group_key() and validate_semantic_join_policy() now branch on connection_mode: direct connectors keep one bucket per connector_id; MCP connectors key every asset individually. The graph UI still colors/legends by source_label (so an MCP toolbox reads as one color, not N), while arc placement uses the finer-grained group so its tools render as visually distinct, non-linked clusters. Retrieval/generation itself was independently verified NOT to have the original cross-connector problem — see the grouping row in §4 below. Nineteenth-pass addendum: the grouping/coloring above was correct but the label rendering wasn't — a fixed 900×460 canvas and a hardcoded 14px label offset meant a real ~33-node catalog (this session's live test) produced overlapping text once more than a handful of nodes shared a tight angular range, independent of the grouping fix. SemanticGraphPanel now scales canvas radius with node count, staggers label offsets for nodes placed close together on the ring (deterministic, no DOM measurement), and adds a node filter box and manual zoom for dense graphs. Verified live against the 24-inferred-edge/33-node catalog: labels no longer overlap and the filter correctly dims non-matching nodes without reflowing the layout
Recurring schedules + watermarks | Done | /schedules/*, Temporal-backed, 15s poll
External DB extraction to staging | Done | staging.py — real, tested, read-only-enforced
Schema drift detection + acknowledgment | Done | /schema-drift, /schema-drift/{id}/acknowledge
Agent registry (versioned instructions, tools, publish) | Done | /agents/*
Agent execution of governed SQL query tools | Done | AgentDefinition/AgentVersion.query_tool_names — bounded run invokes published QueryTools through the same PII-masked, read-only path the external gateway uses
Agent scorecard + governed promotion recommendation | Done | GET /agents/{id}/scorecard — pass_rate >=80% AND zero golden-failure rule; never auto-publishes
Bounded agent orchestration via Temporal (<=12 tool calls) | Done | /agents/runs, temporal_activities.py
Internal tool registry (built-in + allowlisted HTTP) | Done | All 10 seeded tools now have real ToolVersion/handlers (sql.generate, file.profile, quality.run, pipeline.stage, schedule.run were previously unimplemented)
External query-tool gateway (REST/OpenAPI/MCP) | Done | /query-tools/*, /external/v1/*, /mcp, /.well-known/mcp.json
External gateway rate limiting | Done | app/rate_limit.py — Redis-backed fixed window, 60/client/min default, fails open if Redis unreachable
Query-tool creation wizard | Done | relation-options + wizard/preview back a full guided UI
Query-tool lifecycle (draft -> tested -> published -> retired) | Done | /query-tools/{id}/test, /publish, /retire
Jobs, cancel/retry/diagnose, incidents | Done | /jobs/*, /incidents/*
Approvals | Done | /approvals/*
Artifacts: versions, diffs, comments, reviews | Done | /artifacts/*
Governed notebooks (markdown/SQL/restricted Python) | Done | /notebooks/*
Evaluations, replay, red-team suite, baselines | Done | /evaluations/*
Prompt versioning + rollback | Done | /prompts/*
Feedback -> human-review learning-suggestion queue, with trend detection | Done | Repeats within a 30-day window fold into one suggestion with occurrence_count/severity
Role-based landing pages | Done | roleLanding[user.role] in lib/constants.tsx, applied on login
SQL "Why this result?" explainability drawer | Done | SQLView.tsx — source/connector, model provider, validation status/risk/row-limit, grounding evidence
Retention policies | Done | /retention-policies/*
Audit event log | Done | /audit
Semantic metrics + approved joins, metric-to-asset binding | Done | /semantic/*, SemanticMetric.asset_id
Optional embedded Superset (guest token + editor handoff) | Done | /analytics/*, superset_client.py
Superset linking for SQL/notebook results ("publish, hotlink") | Done | Real bug fixed — each published query now gets its own dashboard (was silently overwriting the project's main dashboard); "Open in Superset" hotlink added to SQLView/NotebooksView
Security posture dashboard (prompt-injection / PII / toxic-content scoring) | Done | /security-overview, keyword-classified Incident records
Conversation/SQL quick actions (publish as tool, eject to notebook, rename, feedback) | Done | All 4 were broken on arrival — payload/endpoint mismatches fixed; "Convert to pipeline" removed (no real backend equivalent) rather than faked
Dataset -> "Start analysis" deep link | Done | DatasetsView.tsx onStartAnalysis seeds ConversationsView with a pre-filled question
Search/filter boxes on Approvals, Artifacts, Jobs, Pipelines, Quality, Semantic | Done | Client-side filtering, consistent styling
Quality rule deletion | Done | DELETE /quality/rules/{rule_id} — endpoint existed, now exposed in UI
Agent self-healing on tool-call failure | Done | _reflect_on_tool_error() — model gets tool schema + error text, corrected params re-validated against the same guard as the primary parameter-fill tier
Agent plan reviewer/critic loop | Done | _review_plan_outputs() — may propose up to 2 additional steps from the run's enabled agent set; still flows through normal approval gating
Graph-based multi-hop join pathfinding for grounding | Done | _find_graph_join_paths() — graph walk over SemanticJoinPolicy edges to surface indirect join chains (A->B->C->D)
Gemini model provider configured and tested | Done | Gemini 3.6 Flash and Gemini 3.5 Flash both tested Healthy against the live Gemini API (real GEMINI_API_KEY, not the local deterministic mock); Gemini 3.5 Flash set as the active default provider and used to run a live agent execution
MCP-mode connector to an external MCP Toolbox source | Done (with caveat) | Added "Payments MCP Toolbox" connector (connection_mode=mcp, http://mcp-toolbox:5000/mcp) via the documented flow. Creation and Temporal-backed scan-with-retry both worked as designed. Scan itself failed after 5 retries -- DNS never resolved "mcp-toolbox", meaning that container is not up in this environment (its image is a private Google Artifact Registry path, most likely needs gcloud auth configure-docker). Infra/credential gap, not a DataPilot code defect.
External query-tool registry actually exposing a tool to an external agent | Done | Registered a real "Postgres demo warehouse" connector (postgres-demo container, real seeded demo.customers/orders/payments data) since the only pre-existing connectors were either credential-less (schema-browsing only) or unreachable (MCP Toolbox). Built customers.lookup via the Catalog wizard, tested it live (returned 1 real row), published it, created an external client with a bearer token, and granted the tool to that client -- the full draft-to-tested-to-published-to-granted lifecycle now proven against real data.
Full bounded-agent execution captured end to end | Done | Ran "Profile demo.customers: row count, null rates, and the distribution of customer_id" from the Workspace ask box. Plan/trace shows Planner -> Metadata -> SQL Analyst -> Quality -> Policy, all COMPLETE; run correctly paused at "WAITING FOR APPROVAL" (deterministic policy gate, HIGH risk), was approved via the Approvals inbox, and the job reached SUCCEEDED with 11 evidence items and a full execution log.
Catalog + semantic-graph export | ✅ New this session | The backend Data Package export (GET /datapackage, GET /datasets/{id}/datapackage, frictionless.py) existed with no frontend button — DatasetsView.tsx now has "Export CSV" (client-side, one row per column: schema/table/column/type/business_name/description/tags/owner/sensitivity/status) and "Export data package" (downloads the existing JSON endpoint's response). SemanticGraphPanel (SemanticView.tsx) gained "Export graph data (JSON)" and "Export as SVG" (a visual snapshot only — the exported file doesn't carry globals.css's node/edge styling, so it renders unstyled outside the app; noted inline in the code)
LLM-suggested table/column descriptions | ✅ New this session | app/metadata_generation.py's suggest_dataset_metadata() asks the project's routed model (new purpose metadata_generation) for a table description plus per-column business_name/description, from column names/types only — never sample row values, since a description doesn't need them and they could carry PII into a third-party call. Auto-applied (status ai_suggested) the first time a table is discovered via connector scan (metadata_scan_runtime.py) or file ingest/staging (routers/files.py, both the direct-ingest and mapped-staging paths), gated by is_unreviewed_description() so a rescan can never clobber a human-written or already-suggested description — a real overwrite bug in this exact gate was found and fixed mid-session (see change log). Also exposed as an on-demand POST /datasets/{asset_id}/generate-metadata ("Generate with AI" in the Review-metadata modal) that returns a suggestion for the human to edit/save through the existing flow rather than writing to the DB itself; saving an ai_suggested dataset without picking a different status auto-promotes it to reviewed. 9 new unit tests (test_metadata_generation.py) cover empty/malformed/erroring provider responses, an invented column name being dropped, and description truncation
Paste-your-own-SQL explain/validate mode | ✅ New this session | POST /sql/explain (routers/sql.py) lets a user paste a hand-written statement instead of asking in natural language: runs the exact same read-only/catalog-only guard as generation (_safe_read_only_sql + unknown_relations, scoped through catalog_scope.queryable_asset_ids like /sql/generate), then asks the model to explain it in business terms and returns a response shaped exactly like /sql/generate's so the SQL workspace's existing evidence/preview panels render it with no new UI logic. SQLView.tsx gets an "Ask a question" / "Paste SQL" mode toggle plus a "Save as verified query" action that registers the explained SQL through the existing POST /verified-queries. The NL path also gained an optional "Add extra context" field folded into the question text sent to /sql/generate — no backend schema change needed

## Enterprise Readiness
2. Enterprise Readiness
Certification, security, and production-hardening posture — what an enterprise buyer or security review would ask about first.
Capability | Status | Evidence / Gap
Live SQL Server / Oracle / Teradata / BigQuery certification | Partial | SQL Server unblocked this pass — self-contained Docker container (sqlserver-demo) + MCP-mode path, no host config needed. Not yet run live from the doc-authoring sandbox (no Docker daemon there). Oracle/Teradata/BigQuery remain fully open — drivers installed, unit-exercised only, no live instance
PingFederate / SSO end-to-end | Not started | Admin config contract exists; full OIDC login/callback/logout/group-mapping not wired
Fine-grained RBAC | Partial | require_permission() checks project-membership role, wired into 8 routers. One remaining spot: artifacts.py's POST /artifacts/{id}/review still gates on a raw user.role check, bypassing project-membership role
Production hardening (secrets, TLS/ingress, backup/restore, DR) | Partial | Non-root Dockerfiles, securityContext on every Deployment, worker+web HPAs, worker PDB+liveness probe, tunable DB pool sizing, ingress.example.yaml. Still missing: NetworkPolicy, secrets-manager integration, backup/restore or DR drill, security review
Security review (threat model, pen test, dependency scan) | Not started | Not performed
Self-learning / auto-adaptation | Partial | By design: accepting a suggestion never changes runtime behavior automatically (verified by reading review_learning_suggestion()). Repeated signals aggregate with occurrence_count/severity; full review UI with deep links exists
Registry usability (marketplace view, certification lifecycle) | Done | Lifecycle states (draft/tested/published/retired) and per-tool analytics done; external search by purpose/source/LOB/owner/tags works over /external/v1 and MCP. Proven end-to-end this session: real connector -> tool created -> live test succeeded -> published -> external client created -> tool granted. Still missing: internal search/filter-by-tag control in admin.tsx
Per-connector concurrent-connection ceiling for external MCP/agent traffic | Done | app/connection_guard.py — BoundedSemaphore per connector_id, default 8 (CONNECTOR_MAX_CONCURRENT_CONNECTIONS), 503 with retry message on exceed, not a silent hang or connection storm
Long-running external extraction (source -> staging) durability | Done | POST /extractions/{id}/run now Temporal-dispatch-first (ExternalExtractionWorkflow) with sync fallback — matches the pattern every other ingestion path already used
Message queue / Kafka | Done | Answered, not a gap: Temporal already serves as the durable async engine; Redis covers cross-request state. Kafka would only earn its place for genuine multi-consumer event fan-out, which nothing in the product needs yet
Scalability | Partial | Architecturally sound (stateless API/web pods scale via HPA, Temporal workers scale independently) but not load-tested. One documented, unresolved capacity risk: Postgres connection exhaustion at max replica counts (144 possible connections vs. Postgres default max_connections=100)
CI pipeline | Done | .github/workflows/ci.yml — pytest + tsc --noEmit / next build on every push/PR

## Engineering Health
3. Engineering / Codebase Health
Test coverage, architecture, and documentation hygiene.
Item | Status | Detail
Backend test suite | Done | 67/68 passing, 1 skipped (test_api.py + test_connection_guard.py), ~9s
Backend architecture | Done | main.py (was 7,069 lines / one file) restructured into a shared module + 25 domain-scoped routers/*.py files; stable across 4+ rounds of concurrent changes
Test coverage breadth | Partial | Single primary test file against 170+ endpoints. Missing dedicated coverage: /lineage/graph, /semantic/graph, /sql/history, /datasets/import, PII masking behavior, RBAC permission-map paths
Frontend architecture | Done | page.tsx (was 2,714 lines) restructured into a composition root + types.ts + lib/constants.tsx + 20 component files; tsc --noEmit clean
Repo cleanliness | Partial | Empty leftover scaffold dirs (apps/web/db, apps/web/worker, apps/web/drizzle, apps/web/app/_sites-preview) remain — permission-locked, needs manual removal from Explorer
Deployment security posture (OCP/K8s) | Done | Non-root Dockerfiles, securityContext on every Deployment, worker/web HPAs, worker PDB + liveness probe, tunable pool sizing, ingress.example.yaml
Demo video | Not started | docs/videos/ was placeholder only as of the last code-level pass. Not recorded yet this session either — deprioritized in favor of the 3 deliverables (this tracker, the consolidated demo doc, the updated PPT) plus the 17 real screenshots below
Screenshots | Done | UPGRADED this session: 32 real screenshots captured by driving the live running app (Chrome, localhost:3000), saved to docs/screenshots/workflows/ — full admin walkthrough (steps 00-13), 3 persona landing pages, plus complete coverage of every remaining nav section (Semantic layer, Tool registry x2, all 6 Admin sub-tabs, Evaluations, live embedded Superset, Analysis, Notebooks, Datasets, Jobs, Artifacts)

## Metadata Q&A
4. Metadata Management — Direct Answers
Common product questions, answered directly against the code rather than assumed.
Question | Status | Answer
How does DataPilot pull metadata from a source database? | Done | Admin adds a Connector (direct driver or MCP mode), calls POST /connectors/{id}/scan -> discover_metadata(), writes/updates DataAsset rows, raises SchemaDriftEvent on column changes
Can metadata be scanned through an MCP-connected source? | Done | discover_mcp_metadata() catalogs each upstream tool's schema as a queryable asset with inferred PII/date/id tags
Can I upload metadata instead of connecting live? | Done | POST /datasets/import accepts a CSV, creates/updates DataAsset rows tagged metadata_status="manual_import", no live connection required
Can I manually edit or review scanned metadata (description, tags, owner, sensitivity, freshness, status)? | Done | PUT /datasets/{asset_id} — API and the DatasetsView.tsx edit modal both cover all six fields
Is discovered/ingested metadata flagged for PII? | Done | annotate_columns() in app/pii.py tags columns with sensitivity: "pii" + pii_category during file ingestion and connector metadata discovery
Is metadata scoped per project? | Done | DataAsset.project_id / Connector.project_id are FKs, every route filters by require_current_project(). No cross-project catalog sharing
Can one project have multiple sets of joined tables, or multiple "data models"/groupings? | Not started | Confirmed no such concept exists in code — a project's catalog is a flat list of DataAsset rows. Only grouping primitives are free-text tags and schema_name. No first-class "data model"/"domain" object. This is a design decision (new entity + migration + UI), not a bug
Where are business names for tables/columns stored, and do they reach the vector store? | Done | Postgres (DataAsset.description, DataAsset.columns JSON) is the source of truth; reaches Qdrant via index_document(). embed_text() now calls the active ModelProvider's real embeddings API (Gemini / OpenAI / OpenAI-compatible) using ModelProvider.embedding_model — falls back to a deterministic hash only when no provider/secret is configured or the provider type has no embeddings API

## Bugs Found Live
Bugs Found by Driving the Live App (this session)
Found by actually clicking through the running app end to end — not by reading code. Both are real, reproducible issues.
Bug | Status | Symptom | Root cause | Fix / next step | Screenshot(s)
SQL generation / "Ask a question" returns 500 | Fix written, pending redeploy | TypeError: Object of type datetime is not JSON serializable | Both POST /sql/generate and POST /conversations/{id}/messages execute a query locally (staging.py's execute_parameterized_read_only) and persist the raw result verbatim into a JSONB column (QueryRun.result / SqlQueryCache.result). Raw driver values for date/time/decimal columns come back as native Python datetime/Decimal objects, which psycopg's JSON adapter cannot serialize — every call that touched such a column failed on commit. | Added _json_safe_value() in apps/api/app/staging.py, applied to every row before it's masked/stored (mirrors the existing _coerce() pattern already used for file-ingestion type coercion). Code fix is in place; the api container has no source bind-mount, so it requires docker compose up --build -d api worker to take effect. Re-tested live after the user's rebuild attempt — still reproducing (3x fresh 500 on /api/sql/generate), so the rebuild has not completed/landed yet as of this tracker. | 06-ask-question-ERROR-bug.png, 07-sql-generate-ERROR-bug.png
Quality rule run shows contradictory pass rate and status | Fix written, pending redeploy | "Pass rate: 100%" and "Status: ERROR" both shown simultaneously, with a toast reading "0 rows passed" | Two layers: (1) QualityRun.pass_rate/checked_rows/failed_rows default to 100.0/0/0; run_quality_rule()'s exception handler set status="error" but never touched those fields, so any errored run displayed the model defaults regardless of what happened. (2) execute_quality_rule() always queries the app's own local Postgres engine, never the asset's actual connector — an external-source asset that was never staged locally has no matching local table, so the run threw an opaque error with no hint that staging is the fix. | Fixed in apps/api/app/routers/quality.py's run_quality_rule(): the exception handler now zeroes checked_rows/failed_rows/pass_rate on any failure, and an asset with a connector_id now raises a clear "stage this table first" error instead of an opaque reflection failure. Same deployment constraint as bug #1 — needs a container rebuild, not yet verified live (no Python deps available in this sandbox to unit-test). | 10-quality-rules.png
Query-tool "Test" button returns bare 500 on any failure | Fixed, pending redeploy | POST /query-tools/{id}/test against a connector with no usable credentials (e.g. the demo-only "Banking demo warehouse") returned a bare "Internal Server Error" with zero diagnostic detail | test_query_tool() in routers/query_tools.py called execute_connector_query() with no try/except, so any exception propagated unhandled. The sibling external-invoke path (_invoke_external_query_tool in main.py) already had this exact handling and converts the same failure into an informative 422 -- the internal Test button never got the equivalent fix. | Wrapped the call in try/except mirroring the invoke path: raises HTTPException(422, f"Query tool test failed: {exc}") with the real error text. Verified the surrounding capability works correctly once pointed at a connector with real credentials (new Postgres demo warehouse connector, live test returned 1 row). Needs the same container rebuild as bugs #1-2 to take effect. | 32-query-tool-live-test-success.png

## Priority Order
7. Recommended Priority Order
What to close next, ranked by what it unblocks.
Priority | Category | Status | Items
P0 | Security hygiene (user action) | Not started | Rotate the Gemini and OpenRouter API keys shared in chat; change the seeded admin's temporary password; commit the September review work (nothing is committed yet).
P0 | Good demo | Not started | Record the actual demo video. Screenshots DONE this session — 32 captured, full application coverage (up from 17). Run one live SQL Server scan end-to-end (direct + MCP) against the now-unblocked sqlserver-demo container
P0 | Enterprise credibility | Not started | SSO completion, live connector certification beyond SQL Server (Oracle/Teradata/BigQuery), a real security review/pen test, a NetworkPolicy, a backup/restore drill
P1 | Correctness / trust | Partial | artifacts.py's approval-decision endpoint is the one remaining raw user.role check (real migration gap). Re-verify require_permission/project_permissions/current_membership imports stay intact after future refactors. Give tests/test_new_endpoints.py its own isolated DATABASE_URL. Add automated PII-masking tests
P1 | Scale-readiness | Not started | Load-test against the documented Postgres connection-pool math before raising HPA maxReplicas. Add a NetworkPolicy. Consider a custom Temporal-queue-depth autoscaling metric for the worker
P1 | Usability | Not started | Add filter controls to the query-tool gateway list — the one remaining piece of "registry marketplace" polish
P1 | Maintainability | Done | main.py and page.tsx split into per-domain/per-view modules, verified stable across 4+ rounds of unrelated concurrent changes
P2 | Embedding model wiring | Done | ModelProvider.embedding_model now actually wired into vector_store.embed_text() for Gemini/OpenAI/OpenAI-compatible, with dimension-safe reindexing. Remaining open item: a first-class grouping entity if multi-model-per-project becomes a real requirement